## Sheet1
Sno | Task | Start Date | End Date | Status
GMS Automation Milestone Release
1 | Discovery, Documentation & Planning | 2023-03-07 | 07-14-2023
1.1 | Module Requirements Collection | 2023-03-07 | 07-14-2023 | Completed
1.2 | Requirements Documentation | 2023-03-07 | 07-14-2023 | Completed
2 | CLIN1 | 2023-12-06 | 06-16-2023
2.1 | Document CLIN1 Requirements | 2023-12-06 | 06-13-2023 | Completed
2.2 | CLIN1 Automation Script Development | 2023-12-06 | 06-14-2023 | Completed
2.3 | CLIN1 Script Checkin & Validation (local) | 06-15-2023 | 06-16-2023 | Completed
2.4 | CLIN1 Script Release | 07-13-2023 | 07-13-2023 | Completed
2.5 | CLIN1 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
2.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
3 | CLIN2 | 2023-12-06 | 06-16-2023
3.1 | Document CLIN2 Requirements | 2023-12-06 | 06-13-2023 | Completed
3.2 | CLIN2 Automation Script Development | 2023-12-06 | 06-14-2023 | Completed
3.3 | CLIN2 Script Checkin & Validation (local) | 06-15-2023 | 06-16-2023 | Completed
3.4 | CLIN2 Script Release | 07-13-2023 | 07-13-2023 | Completed
3.5 | CLIN2 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
3.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
4 | TRAN1 | 06-19-2023 | 06-23-2023
4.1 | Document TRAN1 Requirements | 06-19-2023 | 06-20-2023 | Completed
4.2 | TRAN1 Automation Script Development | 06-19-2023 | 06-21-2023 | Completed
4.3 | TRAN1 Script Checkin & Validation (local) | 06-22-2023 | 06-23-2023 | Completed
4.4 | TRAN1 Script Release | 07-13-2023 | 07-13-2023 | Completed
4.5 | TRAN1 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
4.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
5 | TRAN2 | 06-19-2023 | 06-23-2023
5.1 | Document TRAN2 Requirements | 06-19-2023 | 06-20-2023 | Completed
5.2 | TRAN2 Automation Script Development | 06-19-2023 | 06-21-2023 | Completed
5.3 | TRAN2 Script Checkin & Validation (local) | 06-22-2023 | 06-23-2023 | Completed
5.4 | TRAN2 Script Release | 07-13-2023 | 07-13-2023 | Completed
5.5 | TRAN2 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
5.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
6 | TRAN3 | 06-19-2023 | 06-23-2023
6.1 | Document TRAN3 Requirements | 06-19-2023 | 06-20-2023 | Completed
6.2 | TRAN3 Automation Script Development | 06-19-2023 | 06-21-2023 | Completed
6.3 | TRAN3 Script Checkin & Validation (local) | 06-22-2023 | 06-23-2023 | Completed
6.4 | TRAN3 Script Release | 07-13-2023 | 07-13-2023 | Completed
6.5 | TRAN3 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
6.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
7 | TRAN4 | 06-26-2023 | 06-30-2023
7.1 | Document TRAN4 Requirements | 06-26-2023 | 06-27-2023 | Completed
7.2 | TRAN4 Automation Script Development | 06-26-2023 | 06-28-2023 | Completed
7.3 | TRAN4 Script Checkin & Validation (local) | 06-29-2023 | 06-30-2023 | Completed
7.4 | TRAN4 Script Release | 07-13-2023 | 07-13-2023 | Completed
7.5 | TRAN4 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
7.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
8 | DISC0 | 06-26-2023 | 06-30-2023
8.1 | Document DISC0 Requirements | 06-26-2023 | 06-27-2023 | Completed
8.2 | DISC0Automation Script Development | 06-26-2023 | 06-28-2023 | Completed
8.3 | DISC0 Script Checkin & Validation (local) | 06-29-2023 | 06-30-2023 | Completed
8.4 | DISC0 Script Release | 07-13-2023 | 07-13-2023 | Completed
8.5 | DISC0 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
8.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
9 | DISC2 | 06-26-2023 | 06-30-2023
9.1 | Document DISC2 Requirements | 06-26-2023 | 06-27-2023 | Completed
9.2 | DISC2 Automation Script Development | 06-26-2023 | 06-28-2023 | Completed
9.3 | DISC2 Script Checkin & Validation (local) | 06-29-2023 | 06-30-2023 | Completed
9.4 | DISC2 Script Release | 07-13-2023 | 07-13-2023 | Completed
9.5 | DISC2 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
9.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
10 | EDUC1.10 | 2023-12-06 | 06-16-2023
10.1 | Document EDUC1.10 Requirements | 2023-12-06 | 06-13-2023 | Completed
10.2 | EDUC1.10 Automation Script Development | 2023-12-06 | 06-14-2023 | Completed
10.3 | EDUC1.10 Script Checkin & Validation (local) | 06-15-2023 | 06-16-2023 | Completed
10.4 | EDUC1.10 Script Release | 07-13-2023 | 07-13-2023 | Completed
10.5 | EDUC1.10 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
10.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
11 | EDUC2 | 2023-03-07 | 2023-07-07
11.1 | Document EDUC2 Requirements | 2023-03-07 | 2023-04-07 | Completed
11.2 | EDUC2 Automation Script Development | 2023-03-07 | 2023-05-07 | Completed
11.3 | EDUC2 Script Checkin & Validation (local) | 2023-06-07 | 2023-07-07 | Completed
11.4 | EDUC2 Script Release | 07-13-2023 | 07-13-2023 | Completed
11.5 | EDUC2 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
11.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
12 | EDUC3 | 2023-03-07 | 2023-07-07
12.1 | Document EDUC3 Requirements | 2023-03-07 | 2023-04-07 | Completed
12.2 | EDUC3 Automation Script Development | 2023-03-07 | 2023-05-07 | Completed
12.3 | EDUC3 Script Checkin & Validation (local) | 2023-06-07 | 2023-07-07 | Completed
12.4 | EDUC3 Script Release | 07-13-2023 | 07-13-2023 | Completed
12.5 | EDUC3 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
12.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
13 | EDUC4 | 2023-03-07 | 2023-07-07
13.1 | Document EDUC4 Requirements | 2023-03-07 | 2023-04-07 | Completed
13.2 | EDUC4 Automation Script Development | 2023-03-07 | 2023-05-07 | Completed
13.3 | EDUC4 Script Checkin & Validation (local) | 2023-06-07 | 2023-07-07 | Completed
13.4 | EDUC4 Script Release | 07-13-2023 | 07-13-2023 | Completed
13.5 | EDUC4 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
13.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
14 | EDUC5 | 2023-07-07 | 07-13-2023
14.1 | Document EDUC5 Requirements | 2023-07-07 | 2023-07-07 | Completed
14.2 | EDUC5 Automation Script Development | 2023-07-07 | 07-13-2023 | Completed
14.3 | EDUC5 Script Checkin & Validation (local) | 2023-12-07 | 07-13-2023 | Completed
14.4 | EDUC5 Script Release | 07-13-2023 | 07-13-2023 | Completed
14.5 | EDUC5 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
14.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
15 | INFR4 | 2023-07-07 | 07-13-2023
15.1 | Document INFR4 Requirements | 2023-07-07 | 2023-07-07 | Completed
15.2 | INFR4 Automation Script Development | 2023-07-07 | 07-13-2023 | Completed
15.3 | INFR4 Script Checkin & Validation (local) | 2023-12-07 | 07-13-2023 | Completed
15.4 | INFR4 Script Release | 07-13-2023 | 07-13-2023 | Completed
15.5 | INFR4 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
15.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
16 | INFR5 | 2023-07-07 | 07-13-2023
16.1 | Document INFR5 Requirements | 2023-07-07 | 2023-07-07 | Completed
16.2 | INFR5 Automation Script Development | 2023-07-07 | 07-13-2023 | Completed
16.3 | INFR5 Script Checkin & Validation (local) | 2023-12-07 | 07-13-2023 | Completed
16.4 | INFR5 Script Release | 07-13-2023 | 07-13-2023 | Completed
16.5 | INFR5 Script Checkin & Validation (staging) | 07-18-2023 | 07-19-2023 | Completed
16.6 | Sign-Off | 07-20-2023 | 07-20-2023 | Completed
17 | Review Modules for CLIN | 07-17-2023 | 07-21-2023
17.1 | Document - Requirements | 07-17-2023 | 07-18-2023 | Completed
17.2 | Automation Script Development | 07-18-2023 | 07-20-2023 | Completed
17.3 | Script Checkin & Validation (local) | 07-21-2023 | 07-21-2023 | Completed
17.4 | Script Release | 07-31-2023 | 07-31-2023 | Completed
17.5 | Script Checkin & Validation (staging) | 2023-01-08 | 2023-02-08 | Completed
17.6 | Sign-Off | 2023-03-08 | 2023-03-08 | Completed
18 | Review Modules for DISC | 07-24-2023 | 07-28-2023
18.1 | Document - Requirements | 07-24-2023 | 07-25-2023 | Completed
18.2 | Automation Script Development | 07-25-2023 | 07-27-2023 | Completed
18.3 | Script Checkin & Validation (local) | 07-28-2023 | 07-28-2023 | Completed
18.4 | Script Release | 07-31-2023 | 07-31-2023 | Completed
18.5 | Script Checkin & Validation (staging) | 2023-01-08 | 2023-02-08 | Completed
18.6 | Sign-Off | 2023-03-08 | 2023-03-08 | Completed
19 | Award Creation and PFAR for CLIN1 | 07-31-2023 | 2023-08-08
19.1 | Document - Requirements | 07-31-2023 | 2023-01-08 | Completed
19.2 | Automation Script Development | 2023-01-08 | 2023-07-08 | Completed
19.3 | Script Checkin & Validation (local) | 2023-08-08 | 2023-08-08 | Completed
19.4 | Script Release | 08-21-2023 | 08-21-2023 | Completed
19.5 | Script Checkin & Validation (staging) | 08-22-2023 | 08-23-2023 | Completed
19.6 | Sign-Off | 08-24-2023 | 08-24-2023 | Completed
20 | Award Creation and PFAR for EDUC4 | 2023-09-08 | 08-18-2023
20.1 | Document - Requirements | 2023-09-08 | 2023-10-08 | Completed
20.2 | Automation Script Development | 2023-10-08 | 08-17-2023 | Completed
20.3 | Script Checkin & Validation (local) | 08-18-2023 | 08-18-2023 | Completed
20.4 | Script Release | 08-21-2023 | 08-21-2023 | Completed
20.5 | Script Checkin & Validation (staging) | 08-22-2023 | 08-23-2023 | Completed
20.6 | Sign-Off | 08-24-2023 | 08-24-2023 | Completed
21 | Progress reporting and Checklist for CLIN1 | 08-21-2023 | 2023-01-09
21.1 | Document - Requirements | 08-21-2023 | 2023-08-09 | Completed
21.2 | Automation Script Development | 08-22-2023 | 2023-08-09 | Completed
21.3 | Script Checkin & Validation (local) | 2023-01-09 | 2023-08-09 | Completed
21.4 | Script Release | 09-18-2023 | 09-18-2023 | Completed
21.5 | Script Checkin & Validation (staging) | 09-19-2023 | 09-18-2023 | Completed
21.6 | Sign-Off | 09-21-2023 | 09-18-2023 | Completed
22 | Progress reporting and Checklist for EDUC4 | 2023-04-09 | 09-15-2023
22.1 | Document - Requirements | 2023-04-09 | 2023-08-09 | Completed
22.2 | Automation Script Development | 2023-05-09 | 09-15-1013 | Completed
22.3 | Script Checkin & Validation (local) | 09-15-2023 | 09-15-1013 | Completed
22.4 | Script Release | 09-18-2023 | 09-18-2023 | Completed
22.5 | Script Checkin & Validation (staging) | 09-19-2023 | 09-18-2023 | Completed
22.6 | Sign-Off | 09-21-2023 | 09-18-2023 | Completed
23 | Steady-State Phase | 09-25-2023 | 12-15-2023 | In-Progress