## Sheet1
CIRM-WBS
S.No | Work | Hours
1 | User creation | 4hrs
2 | Institution creation | 4hrs
3 | Common script creation | 4hrs
4 | Test data creation | 4hrs
5 | Save the Test data in Json file and use them with data driven method | 8hrs
6 | Implement the data driven concepts in both CLIN1 and CLIN2 Application | 8hrs
7 | Parallel Testing | 4hrs