## Sheet1
Daily Status Report
Project Name : JTB
Date | Modules | Scenario's | Sub level scenario's | Complexity ( low/medium/high) | Responsible Tester | Date of execution( past / present/future) | Status (Pass/Fail/Blocked) | Defect ID and Description | Defect Severity (Low/High/Medium) | Defect ( Open/Assigned to/Closed)
2023-01-09 | JTB-342 | Auto Report Generation | Day/Hours/Month | High | Xavi Ahisha Ancy.J | 2023-01-09 | Fail | Issue will be fixed by developer | High | Open
2023-01-10 | JTB-344 | Hours Chart discrepancy | List Report | High | Xavi Ahisha Ancy.J | 2023-01-10 | 50% testing completed | - | - | -
2023-01-11 | JTB-344 | Hours Chart discrepancy | List Report | High | Xavi Ahisha Ancy.J | 2023-01-11 | 75% testing completed | - | - | -
2023-01-12 | JTB-343 | JTB SSMPropEditor. Troubles with export/import data from Excel | Export and Import data | High | Xavi Ahisha Ancy.J | 2023-01-12 | 25% testing Completed | - | - | -
Highlights/Issues/Concerns