## Sheet1
Risk Management
Risk Description | Impact Description | Impact | Probability | Trigger Condition | Planned Response | Owner | Mitigation
The client may add more modules for automation scripts. | It will impact the implementation plan and lead to increased effort and budget | High | Medium | They keep on adding more application types | We need to extend the schedule based on their requirements | Excelencia Team | We will create the automation script skeleton and have common scripts ready
The client needs to review all the deliverables and provide their acceptance. If they may make any changes to the automation scripts. | It will affect the implementation plan | High | Medium | Their requirements are not clear. | We need to extend the schedule based on their requirements | Excelencia Team | We will identify alternative workflows and then proceed to develop the common scripts.