## Plan
Parametric Estimation
Sno | Task | Duration | Dependency | Start Date | End Date | Resources
GMS Automation Milestone Release
1 | Discovery, Documentation & Planning | 160 |  | 2023-03-07 | 07-14-2023
1.1 | Module Requirements Collection | 80 | - | 2023-03-07 | 07-14-2023 | T1,T2
1.2 | Requirements Documentation | 80 | 1.1 | 2023-03-07 | 07-14-2023 | T1,T2
2 | CLIN1 | 40 |  | 2023-12-06 | 06-16-2023
2.1 | Document CLIN1 Requirements | 12 | 1.1 | 2023-12-06 | 06-13-2023 | T1
2.2 | CLIN1 Automation Script Development | 24 | 2.1 | 2023-12-06 | 06-14-2023 | T1
2.3 | CLIN1 Script Checkin & Validation (local) | 4 | 2.2 | 06-15-2023 | 06-16-2023 | T2
2.4 | CLIN1 Script Release |  | 2.3 | 07-13-2023 | 07-13-2023 | C1
2.5 | CLIN1 Script Checkin & Validation (staging) |  | 2.4 | 07-18-2023 | 07-19-2023 | C1
2.6 | Sign-Off |  | 2.5 | 07-20-2023 | 07-20-2023 | C1
3 | CLIN2 | 40 |  | 2023-12-06 | 06-16-2023
3.1 | Document CLIN2 Requirements | 12 | 1.1 | 2023-12-06 | 06-13-2023 | T2
3.2 | CLIN2 Automation Script Development | 24 | 3.1 | 2023-12-06 | 06-14-2023 | T2
3.3 | CLIN2 Script Checkin & Validation (local) | 4 | 3.2 | 06-15-2023 | 06-16-2023 | T1
3.4 | CLIN2 Script Release |  | 3.3 | 07-13-2023 | 07-13-2023 | C1
3.5 | CLIN2 Script Checkin & Validation (staging) |  | 3.4 | 07-18-2023 | 07-19-2023 | C1
3.6 | Sign-Off |  | 3.5 | 07-20-2023 | 07-20-2023 | C1
4 | TRAN1 | 40 |  | 06-19-2023 | 06-23-2023
4.1 | Document TRAN1 Requirements | 12 | 1.1 | 06-19-2023 | 06-20-2023 | T1
4.2 | TRAN1 Automation Script Development | 24 | 4.1 | 06-19-2023 | 06-21-2023 | T1
4.3 | TRAN1 Script Checkin & Validation (local) | 4 | 4.2 | 06-22-2023 | 06-23-2023 | T2
4.4 | TRAN1 Script Release |  | 4.3 | 07-13-2023 | 07-13-2023 | C1
4.5 | TRAN1 Script Checkin & Validation (staging) |  | 4.4 | 07-18-2023 | 07-19-2023 | C1
4.6 | Sign-Off |  | 4.5 | 07-20-2023 | 07-20-2023 | C1
5 | TRAN2 | 40 |  | 06-19-2023 | 06-23-2023
5.1 | Document TRAN2 Requirements | 12 | 1.1 | 06-19-2023 | 06-20-2023 | T2
5.2 | TRAN2 Automation Script Development | 24 | 5.1 | 06-19-2023 | 06-21-2023 | T2
5.3 | TRAN2 Script Checkin & Validation (local) | 4 | 5.2 | 06-22-2023 | 06-23-2023 | T1
5.4 | TRAN2 Script Release |  | 5.3 | 07-13-2023 | 07-13-2023 | C1
5.5 | TRAN2 Script Checkin & Validation (staging) |  | 5.4 | 07-18-2023 | 07-19-2023 | C1
5.6 | Sign-Off |  | 5.5 | 07-20-2023 | 07-20-2023 | C1
6 | TRAN3 | 40 |  | 06-19-2023 | 06-23-2023
6.1 | Document TRAN3 Requirements | 12 | 1.1 | 06-19-2023 | 06-20-2023 | T1
6.2 | TRAN3 Automation Script Development | 24 | 6.1 | 06-19-2023 | 06-21-2023 | T2
6.3 | TRAN3 Script Checkin & Validation (local) | 4 | 6.2 | 06-22-2023 | 06-23-2023 | T1
6.4 | TRAN3 Script Release |  | 6.3 | 07-13-2023 | 07-13-2023 | C1
6.5 | TRAN3 Script Checkin & Validation (staging) |  | 6.4 | 07-18-2023 | 07-19-2023 | C1
6.6 | Sign-Off |  | 6.5 | 07-20-2023 | 07-20-2023 | C1
7 | TRAN4 | 40 |  | 06-26-2023 | 06-30-2023
7.1 | Document TRAN4 Requirements | 12 | 1.1 | 06-26-2023 | 06-27-2023 | T1
7.2 | TRAN4 Automation Script Development | 24 | 7.1 | 06-26-2023 | 06-28-2023 | T1
7.3 | TRAN4 Script Checkin & Validation (local) | 4 | 7.2 | 06-29-2023 | 06-30-2023 | T2
7.4 | TRAN4 Script Release |  | 7.3 | 07-13-2023 | 07-13-2023 | C1
7.5 | TRAN4 Script Checkin & Validation (staging) |  | 7.4 | 07-18-2023 | 07-19-2023 | C1
7.6 | Sign-Off |  | 7.5 | 07-20-2023 | 07-20-2023 | C1
8 | DISC0 | 40 |  | 06-26-2023 | 06-30-2023
8.1 | Document DISC0 Requirements | 12 | 1.1 | 06-26-2023 | 06-27-2023 | T2
8.2 | DISC0Automation Script Development | 24 | 8.1 | 06-26-2023 | 06-28-2023 | T2
8.3 | DISC0 Script Checkin & Validation (local) | 4 | 8.2 | 06-29-2023 | 06-30-2023 | T1
8.4 | DISC0 Script Release |  | 8.3 | 07-13-2023 | 07-13-2023 | C1
8.5 | DISC0 Script Checkin & Validation (staging) |  | 8.4 | 07-18-2023 | 07-19-2023 | C1
8.6 | Sign-Off |  | 8.5 | 07-20-2023 | 07-20-2023 | C1
9 | DISC2 | 40 |  | 06-26-2023 | 06-30-2023
9.1 | Document DISC2 Requirements | 12 | 1.1 | 06-26-2023 | 06-27-2023 | T1
9.2 | DISC2 Automation Script Development | 24 | 9.1 | 06-26-2023 | 06-28-2023 | T2
9.3 | DISC2 Script Checkin & Validation (local) | 4 | 9.2 | 06-29-2023 | 06-30-2023 | T1
9.4 | DISC2 Script Release |  | 9.3 | 07-13-2023 | 07-13-2023 | C1
9.5 | DISC2 Script Checkin & Validation (staging) |  | 9.4 | 07-18-2023 | 07-19-2023 | C1
9.6 | Sign-Off |  | 9.5 | 07-20-2023 | 07-20-2023 | C1
10 | EDUC1.10 | 40 |  | 2023-12-06 | 06-16-2023
10.1 | Document EDUC1.10 Requirements | 12 | 1.1 | 2023-12-06 | 06-13-2023 | T1
10.2 | EDUC1.10 Automation Script Development | 24 | 10.1 | 2023-12-06 | 06-14-2023 | T2
10.3 | EDUC1.10 Script Checkin & Validation (local) | 4 | 10.2 | 06-15-2023 | 06-16-2023 | T1
10.4 | EDUC1.10 Script Release |  | 10.3 | 07-13-2023 | 07-13-2023 | C1
10.5 | EDUC1.10 Script Checkin & Validation (staging) |  | 10.4 | 07-18-2023 | 07-19-2023 | C1
10.6 | Sign-Off |  | 10.5 | 07-20-2023 | 07-20-2023 | C1
11 | EDUC2 | 40 |  | 2023-03-07 | 2023-07-07
11.1 | Document EDUC2 Requirements | 12 | 1.1 | 2023-03-07 | 2023-04-07 | T1
11.2 | EDUC2 Automation Script Development | 24 | 11.1 | 2023-03-07 | 2023-05-07 | T1
11.3 | EDUC2 Script Checkin & Validation (local) | 4 | 11.2 | 2023-06-07 | 2023-07-07 | T2
11.4 | EDUC2 Script Release |  | 11.3 | 07-13-2023 | 07-13-2023 | C1
11.5 | EDUC2 Script Checkin & Validation (staging) |  | 11.4 | 07-18-2023 | 07-19-2023 | C1
11.6 | Sign-Off |  | 11.5 | 07-20-2023 | 07-20-2023 | C1
12 | EDUC3 | 40 |  | 2023-03-07 | 2023-07-07
12.1 | Document EDUC3 Requirements | 12 | 1.1 | 2023-03-07 | 2023-04-07 | T2
12.2 | EDUC3 Automation Script Development | 24 | 12.1 | 2023-03-07 | 2023-05-07 | T2
12.3 | EDUC3 Script Checkin & Validation (local) | 4 | 12.2 | 2023-06-07 | 2023-07-07 | T1
12.4 | EDUC3 Script Release |  | 12.3 | 07-13-2023 | 07-13-2023 | C1
12.5 | EDUC3 Script Checkin & Validation (staging) |  | 12.4 | 07-18-2023 | 07-19-2023 | C1
12.6 | Sign-Off |  | 12.5 | 07-20-2023 | 07-20-2023 | C1
13 | EDUC4 | 40 |  | 2023-03-07 | 2023-07-07
13.1 | Document EDUC4 Requirements | 12 | 1.1 | 2023-03-07 | 2023-04-07 | T1
13.2 | EDUC4 Automation Script Development | 24 | 13.1 | 2023-03-07 | 2023-05-07 | T2
13.3 | EDUC4 Script Checkin & Validation (local) | 4 | 13.2 | 2023-06-07 | 2023-07-07 | T1
13.4 | EDUC4 Script Release |  | 13.3 | 07-13-2023 | 07-13-2023 | C1
13.5 | EDUC4 Script Checkin & Validation (staging) |  | 13.4 | 07-18-2023 | 07-19-2023 | C1
13.6 | Sign-Off |  | 13.5 | 07-20-2023 | 07-20-2023 | C1
14 | EDUC5 | 40 |  | 2023-07-07 | 07-13-2023
14.1 | Document EDUC5 Requirements | 12 | 1.1 | 2023-07-07 | 2023-07-07 | T1
14.2 | EDUC5 Automation Script Development | 24 | 14.1 | 2023-07-07 | 07-13-2023 | T1
14.3 | EDUC5 Script Checkin & Validation (local) | 4 | 14.2 | 2023-12-07 | 07-13-2023 | T2
14.4 | EDUC5 Script Release |  | 14.3 | 07-13-2023 | 07-13-2023 | C1
14.5 | EDUC5 Script Checkin & Validation (staging) |  | 14.4 | 07-18-2023 | 07-19-2023 | C1
14.6 | Sign-Off |  | 14.5 | 07-20-2023 | 07-20-2023 | C1
15 | INFR4 | 40 |  | 2023-07-07 | 07-13-2023
15.1 | Document INFR4 Requirements | 12 | 1.1 | 2023-07-07 | 2023-07-07 | T2
15.2 | INFR4 Automation Script Development | 24 | 15.1 | 2023-07-07 | 07-13-2023 | T2
15.3 | INFR4 Script Checkin & Validation (local) | 4 | 15.2 | 2023-12-07 | 07-13-2023 | T1
15.4 | INFR4 Script Release |  | 15.3 | 07-13-2023 | 07-13-2023 | C1
15.5 | INFR4 Script Checkin & Validation (staging) |  | 15.4 | 07-18-2023 | 07-19-2023 | C1
15.6 | Sign-Off |  | 15.5 | 07-20-2023 | 07-20-2023 | C1
16 | INFR5 | 40 |  | 2023-07-07 | 07-13-2023
16.1 | Document INFR5 Requirements | 12 | 1.1 | 2023-07-07 | 2023-07-07 | T1
16.2 | INFR5 Automation Script Development | 24 | 16.1 | 2023-07-07 | 07-13-2023 | T2
16.3 | INFR5 Script Checkin & Validation (local) | 4 | 16.2 | 2023-12-07 | 07-13-2023 | T1
16.4 | INFR5 Script Release |  | 16.3 | 07-13-2023 | 07-13-2023 | C1
16.5 | INFR5 Script Checkin & Validation (staging) |  | 16.4 | 07-18-2023 | 07-19-2023 | C1
16.6 | Sign-Off |  | 16.5 | 07-20-2023 | 07-20-2023 | C1
17 | Review Modules for CLIN | 40 |  | 07-17-2023 | 07-21-2023
17.1 | Document - Requirements | 12 | 1.1 | 07-17-2023 | 07-18-2023 | T1
17.2 | Automation Script Development | 24 | 17.1 | 07-18-2023 | 07-20-2023 | T1,T2
17.3 | Script Checkin & Validation (local) | 4 | 17.2 | 07-21-2023 | 07-21-2023 | T2
17.4 | Script Release |  | 17.3 | 07-31-2023 | 07-31-2023 | C1
17.5 | Script Checkin & Validation (staging) |  | 17.4 | 2023-01-08 | 2023-02-08 | C1
17.6 | Sign-Off |  | 17.5 | 2023-03-08 | 2023-03-08 | C1
18 | Review Modules for DISC | 40 |  | 07-24-2023 | 07-28-2023
18.1 | Document - Requirements | 12 | 1.1 | 07-24-2023 | 07-25-2023 | T2
18.2 | Automation Script Development | 24 | 18.1 | 07-25-2023 | 07-27-2023 | T1,T2
18.3 | Script Checkin & Validation (local) | 4 | 18.2 | 07-28-2023 | 07-28-2023 | T1
18.4 | Script Release |  | 18.3 | 07-31-2023 | 07-31-2023 | C1
18.5 | Script Checkin & Validation (staging) |  | 18.4 | 2023-01-08 | 2023-02-08 | C1
18.6 | Sign-Off |  | 18.5 | 2023-03-08 | 2023-03-08 | C1
19 | Award Creation and PFAR for CLIN1 | 56 |  | 07-31-2023 | 2023-08-08
19.1 | Document - Requirements | 12 | 1.1 | 07-31-2023 | 2023-01-08 | T1
19.2 | Automation Script Development | 40 | 19.1 | 2023-01-08 | 2023-07-08 | T1,T2
19.3 | Script Checkin & Validation (local) | 4 | 19.2 | 2023-08-08 | 2023-08-08 | T2
19.4 | Script Release |  | 19.3 | 08-21-2023 | 08-21-2023 | C1
19.5 | Script Checkin & Validation (staging) |  | 19.4 | 08-22-2023 | 08-23-2023 | C1
19.6 | Sign-Off |  | 19.5 | 08-24-2023 | 08-24-2023 | C1
20 | Award Creation and PFAR for EDUC4 | 56 |  | 2023-09-08 | 08-18-2023
20.1 | Document - Requirements | 12 | 1.1 | 2023-09-08 | 2023-10-08 | T2
20.2 | Automation Script Development | 40 | 20.1 | 2023-10-08 | 08-17-2023 | T1,T2
20.3 | Script Checkin & Validation (local) | 4 | 20.2 | 08-18-2023 | 08-18-2023 | T1
20.4 | Script Release |  | 20.3 | 08-21-2023 | 08-21-2023 | C1
20.5 | Script Checkin & Validation (staging) |  | 20.4 | 08-22-2023 | 08-23-2023 | C1
20.6 | Sign-Off |  | 20.5 | 08-24-2023 | 08-24-2023 | C1
21 | Progress reporting for CLIN1 | 80 |  | 08-21-2023 | 2023-01-09
21.1 | Document - Requirements | 12 | 1.1 | 08-21-2023 | 08-22-2023 | T1
21.2 | Automation Script Development | 64 | 21.1 | 08-22-2023 | 08-31-2023 | T1,T2
21.3 | Script Checkin & Validation (local) | 4 | 21.2 | 2023-09-01 | 2023-09-18 | T2
21.4 | Script Release |  | 21.3 | 2023-09-18 | 09-18-2023 | C1
21.5 | Script Checkin & Validation (staging) |  | 21.4 | 09-19-2023 | 09-20-2023 | C1
21.6 | Sign-Off |  | 21.5 | 09-21-2023 | 09-21-2023 | C1
22 | Progress reporting for EDUC4 | 80 |  | 2023-04-09 | 09-15-2023
22.1 | Document - Requirements | 12 | 1.1 | 2023-09-04 | 2023-09-05 | T2
22.2 | Automation Script Development | 64 | 22.1 | 2023-09-05 | 09-14-2023 | T1,T2
22.3 | Script Checkin & Validation (local) | 4 | 22.2 | 2023-09-15 | 2023-09-18 | T1
22.4 | Script Release |  | 22.3 | 09-18-2023 | 09-18-2023 | C1
22.5 | Script Checkin & Validation (staging) |  | 22.4 | 09-19-2023 | 09-20-2023 | C1
22.6 | Sign-Off |  | 22.5 | 09-21-2023 | 09-21-2023 | C1
Critical Path- Precedence diagramming method-Start to start relationship
| A |  |  |  | If task 21.3 gets delayed, then our schedule gets delayed
| 2days 8days |  | 12days
|  |  |  | 1day |  | 2days | 1day
B
| 2days 8days |  | 3days
Start
21.1
21.2
21.3
22.1
22.2
22.3
22.4
22.5
22.6
End

## Actual
Sno | Task | Duration | Dependency | Start Date | End Date | Resources | Actual Start Date | Actual End Date | Status
GMS Automation Milestone Release
1 | Discovery, Documentation & Planning | 160 |  | 2023-03-07 | 07-14-2023 |  | 2023-03-07 | 07-14-2023
1.1 | Module Requirements Collection | 80 | - | 2023-03-07 | 07-14-2023 | T1,T2 | 2023-03-07 | 07-14-2023 | Completed
1.2 | Requirements Documentation | 80 | 1.1 | 2023-03-07 | 07-14-2023 | T1,T2 | 2023-03-07 | 07-14-2023 | Completed
2 | CLIN1 | 40 |  | 2023-12-06 | 06-16-2023 |  | 2023-12-06 | 06-16-2023
2.1 | Document CLIN1 Requirements | 12 | 1.1 | 2023-12-06 | 06-13-2023 | T1 | 2023-12-06 | 06-13-2023 | Completed
2.2 | CLIN1 Automation Script Development | 24 | 2.1 | 2023-12-06 | 06-14-2023 | T1 | 2023-12-06 | 06-14-2023 | Completed
2.3 | CLIN1 Script Checkin & Validation (local) | 4 | 2.2 | 06-15-2023 | 06-16-2023 | T2 | 06-15-2023 | 06-16-2023 | Completed
2.4 | CLIN1 Script Release |  | 2.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
2.5 | CLIN1 Script Checkin & Validation (staging) |  | 2.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
2.6 | Sign-Off |  | 2.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
3 | CLIN2 | 40 |  | 2023-12-06 | 06-16-2023 |  | 2023-12-06 | 06-16-2023
3.1 | Document CLIN2 Requirements | 12 | 1.1 | 2023-12-06 | 06-13-2023 | T2 | 2023-12-06 | 06-13-2023 | Completed
3.2 | CLIN2 Automation Script Development | 24 | 3.1 | 2023-12-06 | 06-14-2023 | T2 | 2023-12-06 | 06-14-2023 | Completed
3.3 | CLIN2 Script Checkin & Validation (local) | 4 | 3.2 | 06-15-2023 | 06-16-2023 | T1 | 06-15-2023 | 06-16-2023 | Completed
3.4 | CLIN2 Script Release |  | 3.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
3.5 | CLIN2 Script Checkin & Validation (staging) |  | 3.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
3.6 | Sign-Off |  | 3.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
4 | TRAN1 | 40 |  | 06-19-2023 | 06-23-2023 |  | 06-19-2023 | 06-23-2023
4.1 | Document TRAN1 Requirements | 12 | 1.1 | 06-19-2023 | 06-20-2023 | T1 | 06-19-2023 | 06-20-2023 | Completed
4.2 | TRAN1 Automation Script Development | 24 | 4.1 | 06-19-2023 | 06-21-2023 | T1 | 06-19-2023 | 06-21-2023 | Completed
4.3 | TRAN1 Script Checkin & Validation (local) | 4 | 4.2 | 06-22-2023 | 06-23-2023 | T2 | 06-22-2023 | 06-23-2023 | Completed
4.4 | TRAN1 Script Release |  | 4.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
4.5 | TRAN1 Script Checkin & Validation (staging) |  | 4.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
4.6 | Sign-Off |  | 4.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
5 | TRAN2 | 40 |  | 06-19-2023 | 06-23-2023 |  | 06-19-2023 | 06-23-2023
5.1 | Document TRAN2 Requirements | 12 | 1.1 | 06-19-2023 | 06-20-2023 | T2 | 06-19-2023 | 06-20-2023 | Completed
5.2 | TRAN2 Automation Script Development | 24 | 5.1 | 06-19-2023 | 06-21-2023 | T2 | 06-19-2023 | 06-21-2023 | Completed
5.3 | TRAN2 Script Checkin & Validation (local) | 4 | 5.2 | 06-22-2023 | 06-23-2023 | T1 | 06-22-2023 | 06-23-2023 | Completed
5.4 | TRAN2 Script Release |  | 5.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
5.5 | TRAN2 Script Checkin & Validation (staging) |  | 5.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
5.6 | Sign-Off |  | 5.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
6 | TRAN3 | 40 |  | 06-19-2023 | 06-23-2023 |  | 06-19-2023 | 06-23-2023
6.1 | Document TRAN3 Requirements | 12 | 1.1 | 06-19-2023 | 06-20-2023 | T1 | 06-19-2023 | 06-20-2023 | Completed
6.2 | TRAN3 Automation Script Development | 24 | 6.1 | 06-19-2023 | 06-21-2023 | T2 | 06-19-2023 | 06-21-2023 | Completed
6.3 | TRAN3 Script Checkin & Validation (local) | 4 | 6.2 | 06-22-2023 | 06-23-2023 | T1 | 06-22-2023 | 06-23-2023 | Completed
6.4 | TRAN3 Script Release |  | 6.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
6.5 | TRAN3 Script Checkin & Validation (staging) |  | 6.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
6.6 | Sign-Off |  | 6.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
7 | TRAN4 | 40 |  | 06-26-2023 | 06-30-2023 |  | 06-26-2023 | 06-30-2023
7.1 | Document TRAN4 Requirements | 12 | 1.1 | 06-26-2023 | 06-27-2023 | T1 | 06-26-2023 | 06-27-2023 | Completed
7.2 | TRAN4 Automation Script Development | 24 | 7.1 | 06-26-2023 | 06-28-2023 | T1 | 06-26-2023 | 06-28-2023 | Completed
7.3 | TRAN4 Script Checkin & Validation (local) | 4 | 7.2 | 06-29-2023 | 06-30-2023 | T2 | 06-29-2023 | 06-30-2023 | Completed
7.4 | TRAN4 Script Release |  | 7.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
7.5 | TRAN4 Script Checkin & Validation (staging) |  | 7.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
7.6 | Sign-Off |  | 7.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
8 | DISC0 | 40 |  | 06-26-2023 | 06-30-2023 |  | 06-26-2023 | 06-30-2023
8.1 | Document DISC0 Requirements | 12 | 1.1 | 06-26-2023 | 06-27-2023 | T2 | 06-26-2023 | 06-27-2023 | Completed
8.2 | DISC0Automation Script Development | 24 | 8.1 | 06-26-2023 | 06-28-2023 | T2 | 06-26-2023 | 06-28-2023 | Completed
8.3 | DISC0 Script Checkin & Validation (local) | 4 | 8.2 | 06-29-2023 | 06-30-2023 | T1 | 06-29-2023 | 06-30-2023 | Completed
8.4 | DISC0 Script Release |  | 8.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
8.5 | DISC0 Script Checkin & Validation (staging) |  | 8.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
8.6 | Sign-Off |  | 8.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
9 | DISC2 | 40 |  | 06-26-2023 | 06-30-2023 |  | 06-26-2023 | 06-30-2023
9.1 | Document DISC2 Requirements | 12 | 1.1 | 06-26-2023 | 06-27-2023 | T1 | 06-26-2023 | 06-27-2023 | Completed
9.2 | DISC2 Automation Script Development | 24 | 9.1 | 06-26-2023 | 06-28-2023 | T2 | 06-26-2023 | 06-28-2023 | Completed
9.3 | DISC2 Script Checkin & Validation (local) | 4 | 9.2 | 06-29-2023 | 06-30-2023 | T1 | 06-29-2023 | 06-30-2023 | Completed
9.4 | DISC2 Script Release |  | 9.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
9.5 | DISC2 Script Checkin & Validation (staging) |  | 9.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
9.6 | Sign-Off |  | 9.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
10 | EDUC1.10 | 40 |  | 2023-12-06 | 06-16-2023 |  | 2023-12-06 | 06-16-2023
10.1 | Document EDUC1.10 Requirements | 12 | 1.1 | 2023-12-06 | 06-13-2023 | T1 | 2023-12-06 | 06-13-2023 | Completed
10.2 | EDUC1.10 Automation Script Development | 24 | 10.1 | 2023-12-06 | 06-14-2023 | T2 | 2023-12-06 | 06-14-2023 | Completed
10.3 | EDUC1.10 Script Checkin & Validation (local) | 4 | 10.2 | 06-15-2023 | 06-16-2023 | T1 | 06-15-2023 | 06-16-2023 | Completed
10.4 | EDUC1.10 Script Release |  | 10.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
10.5 | EDUC1.10 Script Checkin & Validation (staging) |  | 10.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
10.6 | Sign-Off |  | 10.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
11 | EDUC2 | 40 |  | 2023-03-07 | 2023-07-07 |  | 2023-03-07 | 2023-07-07
11.1 | Document EDUC2 Requirements | 12 | 1.1 | 2023-03-07 | 2023-04-07 | T1 | 2023-03-07 | 2023-04-07 | Completed
11.2 | EDUC2 Automation Script Development | 24 | 11.1 | 2023-03-07 | 2023-05-07 | T1 | 2023-03-07 | 2023-05-07 | Completed
11.3 | EDUC2 Script Checkin & Validation (local) | 4 | 11.2 | 2023-06-07 | 2023-07-07 | T2 | 2023-06-07 | 2023-07-07 | Completed
11.4 | EDUC2 Script Release |  | 11.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
11.5 | EDUC2 Script Checkin & Validation (staging) |  | 11.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
11.6 | Sign-Off |  | 11.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
12 | EDUC3 | 40 |  | 2023-03-07 | 2023-07-07 |  | 2023-03-07 | 2023-07-07
12.1 | Document EDUC3 Requirements | 12 | 1.1 | 2023-03-07 | 2023-04-07 | T2 | 2023-03-07 | 2023-04-07 | Completed
12.2 | EDUC3 Automation Script Development | 24 | 12.1 | 2023-03-07 | 2023-05-07 | T2 | 2023-03-07 | 2023-05-07 | Completed
12.3 | EDUC3 Script Checkin & Validation (local) | 4 | 12.2 | 2023-06-07 | 2023-07-07 | T1 | 2023-06-07 | 2023-07-07 | Completed
12.4 | EDUC3 Script Release |  | 12.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
12.5 | EDUC3 Script Checkin & Validation (staging) |  | 12.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
12.6 | Sign-Off |  | 12.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
13 | EDUC4 | 40 |  | 2023-03-07 | 2023-07-07 |  | 2023-03-07 | 2023-07-07
13.1 | Document EDUC4 Requirements | 12 | 1.1 | 2023-03-07 | 2023-04-07 | T1 | 2023-03-07 | 2023-04-07 | Completed
13.2 | EDUC4 Automation Script Development | 24 | 13.1 | 2023-03-07 | 2023-05-07 | T2 | 2023-03-07 | 2023-05-07 | Completed
13.3 | EDUC4 Script Checkin & Validation (local) | 4 | 13.2 | 2023-06-07 | 2023-07-07 | T1 | 2023-06-07 | 2023-07-07 | Completed
13.4 | EDUC4 Script Release |  | 13.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
13.5 | EDUC4 Script Checkin & Validation (staging) |  | 13.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
13.6 | Sign-Off |  | 13.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
14 | EDUC5 | 40 |  | 2023-07-07 | 07-13-2023 |  | 2023-07-07 | 07-13-2023
14.1 | Document EDUC5 Requirements | 12 | 1.1 | 2023-07-07 | 2023-07-07 | T1 | 2023-07-07 | 2023-07-07 | Completed
14.2 | EDUC5 Automation Script Development | 24 | 14.1 | 2023-07-07 | 07-13-2023 | T1 | 2023-07-07 | 07-13-2023 | Completed
14.3 | EDUC5 Script Checkin & Validation (local) | 4 | 14.2 | 2023-12-07 | 07-13-2023 | T2 | 2023-12-07 | 07-13-2023 | Completed
14.4 | EDUC5 Script Release |  | 14.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
14.5 | EDUC5 Script Checkin & Validation (staging) |  | 14.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
14.6 | Sign-Off |  | 14.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
15 | INFR4 | 40 |  | 2023-07-07 | 07-13-2023 |  | 2023-07-07 | 07-13-2023
15.1 | Document INFR4 Requirements | 12 | 1.1 | 2023-07-07 | 2023-07-07 | T2 | 2023-07-07 | 2023-07-07 | Completed
15.2 | INFR4 Automation Script Development | 24 | 15.1 | 2023-07-07 | 07-13-2023 | T2 | 2023-07-07 | 07-13-2023 | Completed
15.3 | INFR4 Script Checkin & Validation (local) | 4 | 15.2 | 2023-12-07 | 07-13-2023 | T1 | 2023-12-07 | 07-13-2023 | Completed
15.4 | INFR4 Script Release |  | 15.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
15.5 | INFR4 Script Checkin & Validation (staging) |  | 15.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
15.6 | Sign-Off |  | 15.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
16 | INFR5 | 40 |  | 2023-07-07 | 07-13-2023 |  | 2023-07-07 | 07-13-2023
16.1 | Document INFR5 Requirements | 12 | 1.1 | 2023-07-07 | 2023-07-07 | T1 | 2023-07-07 | 2023-07-07 | Completed
16.2 | INFR5 Automation Script Development | 24 | 16.1 | 2023-07-07 | 07-13-2023 | T2 | 2023-07-07 | 07-13-2023 | Completed
16.3 | INFR5 Script Checkin & Validation (local) | 4 | 16.2 | 2023-12-07 | 07-13-2023 | T1 | 2023-12-07 | 07-13-2023 | Completed
16.4 | INFR5 Script Release |  | 16.3 | 07-13-2023 | 07-13-2023 | C1 | 07-13-2023 | 07-13-2023 | Completed
16.5 | INFR5 Script Checkin & Validation (staging) |  | 16.4 | 07-18-2023 | 07-19-2023 | C1 | 07-18-2023 | 07-19-2023 | Completed
16.6 | Sign-Off |  | 16.5 | 07-20-2023 | 07-20-2023 | C1 | 07-20-2023 | 07-20-2023 | Completed
17 | Review Modules for CLIN | 40 |  | 07-17-2023 | 07-21-2023 |  | 07-17-2023 | 07-21-2023
17.1 | Document - Requirements | 12 | 1.1 | 07-17-2023 | 07-18-2023 | T1 | 07-17-2023 | 07-18-2023 | Completed
17.2 | Automation Script Development | 24 | 17.1 | 07-18-2023 | 07-20-2023 | T1,T2 | 07-18-2023 | 07-20-2023 | Completed
17.3 | Script Checkin & Validation (local) | 4 | 17.2 | 07-21-2023 | 07-21-2023 | T2 | 07-21-2023 | 07-21-2023 | Completed
17.4 | Script Release |  | 17.3 | 07-31-2023 | 07-31-2023 | C1 | 07-31-2023 | 07-31-2023
17.5 | Script Checkin & Validation (staging) |  | 17.4 | 2023-01-08 | 2023-02-08 | C1 | 2023-01-08 | 2023-02-08
17.6 | Sign-Off |  | 17.5 | 2023-03-08 | 2023-03-08 | C1 | 2023-03-08 | 2023-03-08
18 | Review Modules for DISC | 40 |  | 07-24-2023 | 07-28-2023 |  | 07-24-2023 | 07-28-2023
18.1 | Document - Requirements | 12 | 1.1 | 07-24-2023 | 07-25-2023 | T2 | 07-24-2023 | 07-25-2023 | Completed
18.2 | Automation Script Development | 24 | 18.1 | 07-25-2023 | 07-27-2023 | T1,T2 | 07-25-2023 | 07-27-2023 | Completed
18.3 | Script Checkin & Validation (local) | 4 | 18.2 | 07-28-2023 | 07-28-2023 | T1 | 07-28-2023 | 07-28-2023 | Completed
18.4 | Script Release |  | 18.3 | 07-31-2023 | 07-31-2023 | C1 | 07-31-2023 | 07-31-2023
18.5 | Script Checkin & Validation (staging) |  | 18.4 | 2023-01-08 | 2023-02-08 | C1 | 2023-01-08 | 2023-02-08
18.6 | Sign-Off |  | 18.5 | 2023-03-08 | 2023-03-08 | C1 | 2023-03-08 | 2023-03-08
19 | Award Creation and PFAR for CLIN1 | 56 |  | 07-31-2023 | 2023-08-08 |  | 07-31-2023 | 2023-08-08
19.1 | Document - Requirements | 12 | 1.1 | 07-31-2023 | 2023-01-08 | T1 | 07-31-2023 | 2023-01-08 | Completed
19.2 | Automation Script Development | 40 | 19.1 | 2023-01-08 | 2023-07-08 | T1,T2 | 2023-01-08 | 2023-07-08 | Completed
19.3 | Script Checkin & Validation (local) | 4 | 19.2 | 2023-08-08 | 2023-08-08 | T2 | 2023-08-08 | 2023-08-08 | Completed
19.4 | Script Release |  | 19.3 | 08-21-2023 | 08-21-2023 | C1 | 08-21-2023 | 08-21-2023
19.5 | Script Checkin & Validation (staging) |  | 19.4 | 08-22-2023 | 08-23-2023 | C1 | 08-22-2023 | 08-23-2023
19.6 | Sign-Off |  | 19.5 | 08-24-2023 | 08-24-2023 | C1 | 08-24-2023 | 08-24-2023
20 | Award Creation and PFAR for EDUC4 | 56 |  | 2023-09-08 | 08-18-2023 |  | 2023-09-08 | 08-18-2023
20.1 | Document - Requirements | 12 | 1.1 | 2023-09-08 | 2023-10-08 | T2 | 2023-09-08 | 2023-10-08 | Completed
20.2 | Automation Script Development | 40 | 20.1 | 2023-10-08 | 08-17-2023 | T1,T2 | 2023-10-08 | 08-17-2023 | Completed
20.3 | Script Checkin & Validation (local) | 4 | 20.2 | 08-18-2023 | 08-18-2023 | T1 | 08-18-2023 | 08-18-2023 | Completed
20.4 | Script Release |  | 20.3 | 08-21-2023 | 08-21-2023 | C1 | 08-21-2023 | 08-21-2023
20.5 | Script Checkin & Validation (staging) |  | 20.4 | 08-22-2023 | 08-23-2023 | C1 | 08-22-2023 | 08-23-2023
20.6 | Sign-Off |  | 20.5 | 08-24-2023 | 08-24-2023 | C1 | 08-24-2023 | 08-24-2023
21 | Progress reporting for CLIN1 | 80 |  | 08-21-2023 | 2023-01-09 |  | 08-21-2023 | 2023-01-09
21.1 | Document - Requirements | 12 | 1.1 | 08-21-2023 | 08-22-2023 | T1 | 08-21-2023 | 2023-09-04 | Completed
21.2 | Automation Script Development | 64 | 21.1 | 08-22-2023 | 08-31-2023 | T1,T2 | 08-22-2023 | 2023-06-09 | Completed
21.3 | Script Checkin & Validation (local) | 4 | 21.2 | 2023-09-01 | 2023-09-18 | T2 | 2023-09-06 | 2023-09-08 | Completed
21.4 | Script Release |  | 21.3 | 09-18-2023 | 09-18-2023 | C1
21.5 | Script Checkin & Validation (staging) |  | 21.4 | 09-19-2023 | 09-20-2023 | C1
21.6 | Sign-Off |  | 21.5 | 09-21-2023 | 09-21-2023 | C1
22 | Progress reporting for EDUC4 | 80 |  | 2023-04-09 | 09-15-2023 |  | 2023-04-09 | 09-15-2023
22.1 | Document - Requirements | 12 | 1.1 | 2023-09-04 | 2023-05-09 | T2 | 2023-09-04 | 2023-09-05 | Completed
22.2 | Automation Script Development | 64 | 22.1 | 2023-09-05 | 09-14-2023 | T1,T2 | 2023-09-05 | 2023-09-13 | completed
22.3 | Script Checkin & Validation (local) | 4 | 22.2 | 09-15-2023 | 2023-09-18 | T1 | 09-13-2023 |  | 90%completed
22.4 | Script Release |  | 22.3 | 09-18-2023 | 09-18-2023 | C1
22.5 | Script Checkin & Validation (staging) |  | 22.4 | 09-19-2023 | 09-20-2023 | C1
22.6 | Sign-Off |  | 22.5 | 09-21-2023 | 09-21-2023 | C1

## Metrics
CIRM-GMS Application
S.No | Modules | No. of Scripts/Document Delivered | Workflows | User-Undersatnding Document |  | Automation Script
|  |  |  | Status | Completion (%) | Status | Completion (%)
1 | Application Creation and Submission 1. Create the Application. 2. Assign AOO. 3. Submit by PI. 4. Check the Application is available in Grant Application | 15 | CLIN1 | Delivered | 100% | Delivered | 100%
2 |  |  | CLIN2 | Delivered | 100% | Delivered | 100%
3 |  |  | DISC0 | Delivered | 100% | Delivered | 100%
4 |  |  | DISC2 | Delivered | 100% | Delivered | 100%
5 |  |  | EDUC1.10 | Delivered | 100% | Delivered | 100%
6 |  |  | EDUC2 | Delivered | 100% | Delivered | 100%
7 |  |  | EDUC3 | Delivered | 100% | Delivered | 100%
8 |  |  | EDUC4 | Delivered | 100% | Delivered | 100%
9 |  |  | EDUC5 | Delivered | 100% | Delivered | 100%
10 |  |  | INFR4 | Delivered | 100% | Delivered | 100%
11 |  |  | INFR5 | Delivered | 100% | Delivered | 100%
12 |  |  | TRAN1 | Delivered | 100% | Delivered | 100%
13 |  |  | TRAN2 | Delivered | 100% | Delivered | 100%
14 |  |  | TRAN3 | Delivered | 100% | Delivered | 100%
15 |  |  | TRAN4 | Delivered | 100% | Delivered | 100%
16 | Review Module Initiation and Review Meeting 1. Create the Review and Add te applications. 2. Add GWG Member, GWG Board Member and Specialist for the selected Application. 3. Save the Crique for every members. 4. Enter Final Score for every members. 5. Check Final Score and Final DEI Score is avilable in the Review | 2 | CLIN | Delivered | 100% | Delivered | 100%
17 |  |  | DISC | Delivered | 100% | Delivered | 100%
18 | Award Creation and Award Closeout 1. Select the application from Grant Application. 2. Slect the Grant Management Officer and Science Officer. 3. Update the Award Grants, Provision JIT's, PFAR. 4. Select the Financial AOO. 5. Fill PI details and Submit the application by PI and AOO. 6.Fill Grant Management Officer details and Science Officer details and submit the application. 7. Create Aim and Milestone and Payments. 8. Assign Payees and generate the Claim number. | 2 | CLIN1 | Delivered | 100% | Delivered | 100%
19 |  |  | EDUC4 | Delivered | 100% | Delivered | 100%
20 | Progress Report 1.Clinical Quarterly Progress Report. 2. Clinical Quarterly Financial Report. 3. Clinical Operational Milestone Report. 4. Clinical Full Progress Report. 5. Semi-Annual Progress Report. 6. Standard Semi-Annual Financial Report. | 2 | CLIN1 | Delivered | 100% | Delivered | 100%
21 |  |  | EDUC4 | Delivered | 100% | Delivered | 100% (Validation is pending)