## Sheet1
Stakeholder Register
Name | Role | Internal/External | Engagement level | Communication Plan | Current Involvement | Desired Involvement | Action Plan
Alan | Manager/Customer Spoc | External | Promoters | Email/Meeting | Leading | Leading | To improve communication effectively.
Doug | Project Manager | External | Defenders | Email/Meeting | Supportive | Leading | To enhance attention.
Venkat | Customer Spoc | External | Latents | Call/Sync-up | Neutral | Supportive | To improve communication effectively.
Mason | Team Member | External | Audience | Call/Sync-up | Neutral | Supportive | To improve communication effectively.
Rajesh | Team manager | Internal | Defenders | Meeting | Supportive | Leading | Need to have a more extensive discussion about the project.
Ancy | Team Lead | Internal | Promoters
Nagaraj | Team Member | Internal | Promoters | Call/Sync-up | Supportive | Leading | Need to assign more responsibilities.
Deva | Team Member | Internal | Promoters | Call/Sync-up | Supportive | Leading | Need to assign more responsibilities.