## Slide 1: Project Status - CIRM
RAG | Summary | Key Issues & Risks
08th September 2023

## Slide 2: Project Status
Date : 09/08/2023 Baseline Start : 05/19/2023
Workstream : CIRM-GMS (Web) Baseline Finish: 09/22/2023
Lead : Xavi Ahisha Ancy Forecast Finish: 12/15/2023
Project Stage : Implementation (Week 16)
Overall Project Status
Schedule Resource
Financial Quality
Commercial Scope
Overall Summary : Implementation Phase
Progress since last report & Key Achievements:
Developing Automation test script for Checklist of EDUC4 Application.
Discussed the issues that the CIRM team was facing with automation scripts on Linux machines and resolved them.
Got acceptance for the automation scripts in the Application Creation, Review Meeting, and Award Creation modules.
Activities Planned for Next Period:
To complete the Automation Script for Checklist –EDUC4 Application.
To complete the user understanding document for the Checklist module of the EDUC4 Application and obtain verification from CIRM.
To deliver the automation test scripts for progress reporting and the checklist for the CLIN1 Application.
Traffic Lights: R = RED, A = AMBER, G = GREEN
Key Deliverables / Milestones | Owner | FC Date | RAG
Delivered the User Document of Progress reporting and checklist for CLIN1 and EDUC4 Application. | Excelencia Team | 09/08/2023 | G
Delivered the Automation Test Scripts of Progress reporting and checklist for CLIN1 Application. | Excelencia Team | 09/08/2023 | G
To deliver the Automation Test Script and User Understanding Document of Progress reporting and checklist for EDUC4 Application. | Excelencia Team | 09/13/2023 | G
RED – Off-target intervention required GREEN – On-target
AMBER – At risk of missing target BLUE - Completed
Client satisfied with the overall Excelencia progress
Client foreseeing risks or issues with Excelencia Delivery
Client not satisfied with Excelencia Delivery

## Slide 3: Project Key Issues & Risks
Key Issues Requiring Management Attention
Key Risks for Management Attention
ID | Type | Functional Area Impacted | Issue including description of Impact | Actions required to resolve Issue | Date that Issue was raised? | To be resolved by when? | Issue Owner
1 | The table of contents changes for every application. | Development of automation test scripts | Need to identify the correct table of contents for every report. | Discuss with the CIRM team to gain clarity about the table of contents. | 09/05/2023 | - | CIRM Team
2 |  |  |  |  |  |  | 
ID | Risk including description of Impact | Mitigation Actions (or counter-measures) | Likelihood (VH – VL) | Date Raised | Risk Owner
1 | The client may make any changes in the automation test scripts. | Modify the implementation plan and seek acceptance from the CIRM Team. | M | 09/07/2023 | Excelencia Team
2 |  |  |  |  | 
A risk is something that may or may not occur but when it does, it becomes an issue. It may be possible to set actions in place now which reduce the probability of the risk coming to pass, or reduce the impact if it does
Total No of Risks on Risk Register | 0 | No of risks closed within the current period. | 0 | No of risks opened within the current period. | 0

## Slide 4
THANK
YOU!